## 01 Dashboard
FlightPath Infogain — Daily Work Dashboard
Filter: 2026-04-08 to 2026-07-20 · Excludes Sundays, ProductiveIT, personal · 8h + 30m lunch
KPI | Value | Month | Roster hours | OT hours | Phase | Work days | Roster h | OT h
Working days | 84 | 2026-04 | 160 | 12 | Observe · CRM · Sites · Sales dashboards | 39 | 312 | 28
Roster hours | 672 | 2026-05 | 200 | 28 | HDFC script with Vishal (delivered) | 10 | 80 | 20
Beyond hours (OT) | 81.5 | 2026-06 | 200 | 30 | Flipkart gift cards with Vishal | 8 | 64 | 16
Leave days | 3 | 2026-07 | 112 | 11.5 | Flipkart automation + team hiring | 14 | 112 | 6
On movement days | 2 |  |  |  | HR assigned + Flipkart suite / platform | 13 | 104 | 11.5
Total logged hours | 753.5
Category
|  | Category | Hours
|  | Flipkart Automation | 114
|  | Website Design | 106
|  | HDFC Script | 80
|  | Observation & Onboarding | 78
|  | CRM Solution | 78
|  | Sales Sheets & Dashboards | 78
|  | Flipkart Gift Cards | 64
|  | Team Hiring | 56
|  | HR Assigned | 27.5
|  | Platform & VPS | 26
|  | Internal Tools | 24
|  | Team Support | 20
|  | Planning & Review | 2
How to filter in Excel
1) Open sheet '02 Daily Log' — use Excel AutoFilter on Date / Month / Status / Category.
2) Open sheet '03 Monthly Summary' for month-wise totals.
3) Re-export with: python export_excel.py --month 2026-07 or --date 2026-07-20
4) ProductiveIT and personal work are excluded by design.

## 00 How to use
Export & filter guide
Sheets
• 01 Dashboard — KPIs, month chart, category pie, phase table
• 02 Daily Log — every task slot (filter by Date / Month / Status / Category)
• 03 Monthly Summary — month-wise totals
• 04 Day Rollup — one row per day (best for date-wise review)
Date-wise in Excel
1. Open 04 Day Rollup or 02 Daily Log
2. Click the filter arrow on the Date column
3. Pick a single date or a range
Month-wise in Excel
1. Filter the Month column (YYYY-MM) on Daily Log or Day Rollup
2. Or open 03 Monthly Summary
Re-export a focused file from terminal
python export_excel.py
python export_excel.py --month 2026-07
python export_excel.py --date 2026-07-20
python export_excel.py --from 2026-05-24 --to 2026-06-14
Windows: double-click EXPORT-EXCEL.bat
Excluded by design: ProductiveIT*, personal/*, Sundays
Recipient review email: virrdhiman@gmail.com (DRAFT only until you finalize)

## 02 Daily Log
Date | Weekday | Month | Status | Phase | Category | Start | End | Hours | Beyond hours? | Task | Detail
2026-04-08 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-08 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-08 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-08 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-09 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-09 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-09 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-09 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-13 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-13 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-13 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-13 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-14 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-14 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-14 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-14 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-15 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-15 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-15 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-15 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-16 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-16 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-16 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-16 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-20 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-20 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-20 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-20 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-21 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-21 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-21 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-21 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-22 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-22 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-22 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-22 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-23 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-23 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-23 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-23 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-04-27 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-27 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-27 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-27 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-28 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-28 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-28 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-28 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-29 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-29 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-29 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-29 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-04-30 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-04-30 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-04-30 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-04-30 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-04 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-04 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-04 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-04 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-05 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-05 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-05 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-05 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-06 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-06 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-06 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-06 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-07 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-07 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-07 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-07 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-11 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-11 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-11 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-11 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-12 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-12 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-12 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-12 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-13 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-13 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-13 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-13 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-14 | Thursday | 2026-05 | Leave | Observe · CRM · Sites · Sales dashboards | — | — | — | 0 | No | Leave | Approved leave — no work hours.
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-18 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-18 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-18 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-18 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-19 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-19 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-19 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-19 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-20 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-20 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-20 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-20 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-21 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-21 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-21 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-21 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Observation & Onboarding | 09:00 | 11:00 | 2 | No | FlightPath operations observation | Shadowed workflows, tools, and handoffs.
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | CRM Solution | 11:00 | 13:00 | 2 | No | CRM solution design & configuration | Lead capture, stages, sales follow-ups.
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 13:30 | 15:30 | 2 | No | Static website design (batch) | Built toward ~20 static sites for FlightPath.
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Sales Sheets & Dashboards | 15:30 | 17:30 | 2 | No | Sales team sheets & dashboards | Pipeline, targets, daily sales tracking.
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | Website Design | 18:00 | 20:00 | 2 | Yes | Sites/dashboards weekend catch-up | Beyond roster catch-up.
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 09:00 | 11:00 | 2 | No | HDFC script with Vishal | Development, hardening, delivery with Vishal.
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 11:00 | 13:00 | 2 | No | HDFC debugging & dry-run | Failure paths, logging, retry behaviour.
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 13:30 | 15:30 | 2 | No | HDFC delivery & handoff | Runbook and acceptance closed.
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | Team Support | 15:30 | 17:30 | 2 | No | Pair review / support | Environment and integration support.
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | HDFC Script | 18:00 | 20:00 | 2 | Yes | HDFC after-hours delivery push | Continued with Vishal past roster.
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 09:00 | 11:00 | 2 | No | Gift-card flow with Vishal | Create/checkout gift-card paths.
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 11:00 | 13:00 | 2 | No | Gift-card UI & validation | Balances, payment option wiring.
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 13:30 | 15:30 | 2 | No | Gift-card regression | Regression and ops handoff notes.
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Automation | 15:30 | 17:30 | 2 | No | Suite touchpoints | Aligned gift-card module with suite contracts.
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | Flipkart Gift Cards | 18:00 | 20:00 | 2 | Yes | Gift-card after-hours pairing | Extended session past 17:30.
2026-06-15 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-15 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-15 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-15 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-16 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-16 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-16 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-16 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-17 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-17 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-17 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-17 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-18 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-18 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-18 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-18 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Automation after-hours build/test | Extra hours past roster.
2026-06-20 | Saturday | 2026-06 | Leave | Flipkart automation + team hiring | — | — | — | 0 | No | Leave | Approved leave — no work hours.
2026-06-22 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-22 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-22 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-22 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-23 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-23 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-23 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-23 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-24 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-24 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-24 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-24 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-25 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-25 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-25 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-25 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Automation after-hours build/test | Extra hours past roster.
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Automation after-hours build/test | Extra hours past roster.
2026-06-29 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-29 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-29 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-29 | Monday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-06-30 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-06-30 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-06-30 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-06-30 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-07-01 | Wednesday | 2026-07 | Work | Flipkart automation + team hiring | Flipkart Automation | 09:00 | 11:00 | 2 | No | Automation suite build | Checkout, tracking, accounts, queues, workspace.
2026-07-01 | Wednesday | 2026-07 | Work | Flipkart automation + team hiring | Flipkart Automation | 11:00 | 13:00 | 2 | No | Automation test & fixes | Smoke paths, OTP/queue issues.
2026-07-01 | Wednesday | 2026-07 | Work | Flipkart automation + team hiring | Team Hiring | 13:30 | 15:30 | 2 | No | Team hiring support | Screening, interviews, role fit.
2026-07-01 | Wednesday | 2026-07 | Work | Flipkart automation + team hiring | Team Hiring | 15:30 | 17:30 | 2 | No | Shortlist & feedback | Written feedback for leadership/HR.
2026-07-02 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-02 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-02 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-02 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Suite/HR after-hours wrap-up | Beyond roster wrap-up.
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Suite/HR after-hours wrap-up | Beyond roster wrap-up.
2026-07-06 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-06 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-06 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-06 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-07 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-07 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-07 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-07 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-08 | Wednesday | 2026-07 | Leave | HR assigned + Flipkart suite / platform | — | — | — | 0 | No | Leave | Approved leave — no work hours.
2026-07-09 | Thursday | 2026-07 | On Movement | HR assigned + Flipkart suite / platform | Planning & Review | 09:00 | 17:30 | 0 | No | On movement | Travel / movement — attendance only.
2026-07-10 | Friday | 2026-07 | On Movement | HR assigned + Flipkart suite / platform | Planning & Review | 09:00 | 17:30 | 0 | No | On movement | Travel / movement — attendance only.
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Suite/HR after-hours wrap-up | Beyond roster wrap-up.
2026-07-13 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-13 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-13 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-13 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-14 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-14 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-14 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-14 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-15 | Wednesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-15 | Wednesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-15 | Wednesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-15 | Wednesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-16 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-16 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-16 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-16 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Suite/HR after-hours wrap-up | Beyond roster wrap-up.
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Internal Tools | 15:30 | 17:30 | 2 | No | Internal tools / ID card | FlightPath Infogain utilities.
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 18:00 | 20:00 | 2 | Yes | Suite/HR after-hours wrap-up | Beyond roster wrap-up.
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 09:00 | 11:00 | 2 | No | HR-assigned task execution | Process, docs, compliance, coordination.
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Flipkart Automation | 11:00 | 13:00 | 2 | No | Flipkart suite delivery | Checkout, tracking, invoices, OTP, agent, UI.
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Platform & VPS | 13:30 | 15:30 | 2 | No | VPS / platform ops | Health, nginx/SSL, deploys, containers.
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | Planning & Review | 15:30 | 17:30 | 2 | No | Prep for Tarun Sir meeting (Sector 8) | Prepared discussion points for evening meeting.
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | HR Assigned | 18:00 | 19:30 | 1.5 | Yes | Meeting with Tarun Sir — Sector 8 | On-site meeting ~6:00 PM.

## 03 Monthly Summary
Month | Work days | Leave days | Movement days | Roster hours | OT hours | Total hours | Lunch breaks (min)
2026-04 | 20 | 0 | 0 | 160 | 12 | 172 | 600
2026-05 | 25 | 1 | 0 | 200 | 28 | 228 | 750
2026-06 | 25 | 1 | 0 | 200 | 30 | 230 | 750
2026-07 | 14 | 1 | 2 | 112 | 11.5 | 123.5 | 420

## 04 Day Rollup
Date | Weekday | Month | Status | Phase | Roster hours | OT hours | Task count | Focus / notes
2026-04-08 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-09 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-10 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-11 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-13 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-14 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-15 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-16 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-17 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-18 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-20 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-21 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-22 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-23 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-24 | Friday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-25 | Saturday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-04-27 | Monday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-28 | Tuesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-29 | Wednesday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-04-30 | Thursday | 2026-04 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-01 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-02 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-04 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-05 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-06 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-07 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-08 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-09 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-11 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-12 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-13 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-14 | Thursday | 2026-05 | Leave | Observe · CRM · Sites · Sales dashboards | 0 | 0 | 0 | Leave
2026-05-15 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-16 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-18 | Monday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-19 | Tuesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-20 | Wednesday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-21 | Thursday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 0 | 4 | Sales team sheets & dashboards
2026-05-22 | Friday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-23 | Saturday | 2026-05 | Work | Observe · CRM · Sites · Sales dashboards | 8 | 2 | 5 | Sites/dashboards weekend catch-up
2026-05-25 | Monday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-05-26 | Tuesday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-05-27 | Wednesday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-05-28 | Thursday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-05-29 | Friday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-05-30 | Saturday | 2026-05 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-06-01 | Monday | 2026-06 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-06-02 | Tuesday | 2026-06 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-06-03 | Wednesday | 2026-06 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-06-04 | Thursday | 2026-06 | Work | HDFC script with Vishal (delivered) | 8 | 2 | 5 | HDFC after-hours delivery push
2026-06-05 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-06 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-08 | Monday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-09 | Tuesday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-10 | Wednesday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-11 | Thursday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-12 | Friday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-13 | Saturday | 2026-06 | Work | Flipkart gift cards with Vishal | 8 | 2 | 5 | Gift-card after-hours pairing
2026-06-15 | Monday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-16 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-17 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-18 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-19 | Friday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 2 | 5 | Automation after-hours build/test
2026-06-20 | Saturday | 2026-06 | Leave | Flipkart automation + team hiring | 0 | 0 | 0 | Leave
2026-06-22 | Monday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-23 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-24 | Wednesday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-25 | Thursday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-26 | Friday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 2 | 5 | Automation after-hours build/test
2026-06-27 | Saturday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 2 | 5 | Automation after-hours build/test
2026-06-29 | Monday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-06-30 | Tuesday | 2026-06 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-07-01 | Wednesday | 2026-07 | Work | Flipkart automation + team hiring | 8 | 0 | 4 | Shortlist & feedback
2026-07-02 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-03 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 2 | 5 | Suite/HR after-hours wrap-up
2026-07-04 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 2 | 5 | Suite/HR after-hours wrap-up
2026-07-06 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-07 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-08 | Wednesday | 2026-07 | Leave | HR assigned + Flipkart suite / platform | 0 | 0 | 0 | Leave
2026-07-09 | Thursday | 2026-07 | On Movement | HR assigned + Flipkart suite / platform | 0 | 0 | 0 | On movement
2026-07-10 | Friday | 2026-07 | On Movement | HR assigned + Flipkart suite / platform | 0 | 0 | 0 | On movement
2026-07-11 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 2 | 5 | Suite/HR after-hours wrap-up
2026-07-13 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-14 | Tuesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-15 | Wednesday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-16 | Thursday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 0 | 4 | Internal tools / ID card
2026-07-17 | Friday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 2 | 5 | Suite/HR after-hours wrap-up
2026-07-18 | Saturday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 2 | 5 | Suite/HR after-hours wrap-up
2026-07-20 | Monday | 2026-07 | Work | HR assigned + Flipkart suite / platform | 8 | 1.5 | 5 | Meeting with Tarun Sir — Sector 8